## TO DO LIST
Task | Team Member Responsible | Projected Completion
UML Class Relationship Diagram (typed) | Stephanie Krass | 2019-10-24
tPiece | C | 2019-11-08
capLPiece | A | 2019-11-08
mirrorLPiece | A | 2019-11-08
Ipiece | C | 2019-11-08
squarePiece | C | 2019-11-08
sPiece | B | 2019-11-08
zPiece | B | 2019-11-08
Pieces | ABC | 2019-11-12
Point | D | 2019-10-25
Score | E | 2019-11-01
Rules | D | 2019-11-12
Stats | E | 2019-11-08
Board | ABCDE | 2019-11-20
TetrisApp | ABCDE | 2019-11-26
Project Submission Write-up | ABCDE | 2019-11-28
JAR file creation | ABCDE | 2019-11-28
Presentation Document | Non-presenters | 2019-11-28
Presentation Script | presenters | 2019-11-28

## TASK RECORDS
For the final write-up
Task | Team Member Responsible
Project Proposal
Instructions
Description
Problems/ Modifications
Final UML Diagram
PowerPoint Presentation Document
Presentation Script
Executable JAR File